## list
ID | Activity List | Duration | Precedent ID | Relationship | Lead / Lag
id | activity | duration | precedentAct | relationship | L
1 | A | 3 | 0
2 | B | 4 | 1 | FS | 0
3 | C | 2 | 1 | FS | 0
4 | D | 5 | 2 | FS | 0
5 | E | 1 | 3 | FS | 0
6 | F | 2 | 3 | FS | 0
7 | G | 4 | 4,5 | FS,FS | 0,0
8 | H | 3 | 6,7 | FS,FS | 0,0
Note on D1: Enter the ID of precedent activitiy. If there are more than one, enter them in comma separated style. e.g. 1,2. When you enter the first activity, enter 0 and the Relationship and the Lead / Lag column should remain blank.
Note on E1: Enter FS (*Finish to Start), SS (*Start to Start), SF (*Start to Finish) or FF (*Finish to Finish). If there are more than one, enter them in comma separated style. e.g. FS,SS.
Note on F1: When you enter lead time, use negative number. When you enter lag time, use positive number. If there are more than one, enter them in comma separated style. e.g. 1,-2.

## diagram
test
| ID | 1 | Duration | 3
| ES | 0 | EF | 3
A
| LS | 0 | LF | 3
|  |  | (ID_1) FS, 0 |  |  |  | (ID_1) FS, 0
| ID | 2 | Duration | 4 | ID | 3 | Duration | 2
| ES | 3 | EF | 7 | ES | 3 | EF | 5
| B |  |  |  | C
| LS | 3 | LF | 7 | LS | 9 | LF | 11
|  |  | (ID_2) FS, 0 |  |  |  | (ID_3) FS, 0 |  |  |  | (ID_3) FS, 0
| ID | 4 | Duration | 5 | ID | 5 | Duration | 1 | ID | 6 | Duration | 2
| ES | 7 | EF | 12 | ES | 5 | EF | 6 | ES | 5 | EF | 7
| D |  |  |  | E |  |  |  | F
| LS | 7 | LF | 12 | LS | 11 | LF | 12 | LS | 14 | LF | 16
(ID_4) FS, 0 / (ID_5) FS, 0
[5 empty] | ID | 7 | Duration | 4
[5 empty] | ES | 12 | EF | 16
G
[5 empty] | LS | 12 | LF | 16
(ID_6) FS, 0 / (ID_7) FS, 0
[9 empty] | ID | 8 | Duration | 3
[9 empty] | ES | 16 | EF | 19
H
[9 empty] | LS | 16 | LF | 19